Health e Workforce Consortium PM Meeting

May 22, 2013

Web Ex enabled – See invitation for connection instruction

Onsite: V2071

NOTES

| Attended: Toni Mariani; Cindy Woods; Lynnette Bennett; Gregg Sapp; Donna Moran; Maria Anastario; Rachele Bakic; Esther Daniels; Helen Andries; Patricia Dombrowski; Geetha Sukumaran; Matt Kenna; Margaret Murphy; Brooke MacKenzie; Andy Brucia; Nicole Bunselmeyer; Nathan Savage; Michele Royer |  |  |
| --- | --- | --- |
| Agenda Items | Discussion | Action |
| What is the greatest benefit of this project to your college? | Gregg: new hemodialysis focus, moving to new bldg., new partnerships Donna: partnerships with health community, jumpstart u-tech programs Toni: Assoc deg biggest excitement, PLA department excited about PLA, visiting bases with project info Esther: interconnectivity, clarity about curriculum Rachele: articulation, SN going into courses, working with students Maria: outreach is working, radio ad for Med Asst, story about vet, Med Asst program for fall |  |
| Budget Modification Approval All | Can only roll over funds within the same category Patricia will find out how far in advance of Sept 30 will be due | Patricia will send out to MCs |
| Evaluation Contractors Patricia | Orientation meeting set for June 13, July will be BC onsite visit. MC onsite visits TBD Patricia will send out evaluation plan once formed to MCs Evaluation team will join future Consortium meetings. |  |
| VA Approval Call Out | Direct revenue needs to be assigned a code Lynette: event for VA job fair on June 6th Patricia: if we are all in agreement, we could use consortium funds to purchase booth Cindy and Toni: N/A Lynette: approved Gregg: approved Donna: submitted Maria: assume it is approved, will confirm Rachele: waiting to hear, 98% sure it is approved Esther: submitted one, other is waiting for state approval, will submit in Jul | Geetha will send details out to MCs Helen will send out survey re: participation/interest |
| Curriculum Margaret New HIT certificate programs We need to ensure that we have a credible volume of course materials for dissemination. (CAHIMS + course outlines of pre-existing IT courses is not sufficient) | IT and CAHIMS need additional resources. All courses including infused need credible volume of activities. If you have questions, ask Margaret. |  |
| PLA Andy PLA data tracking: any follow up questions? |  | Andy will put materials up on hiteducation.org site |
| Data & Compliance Reminder: Contact Matt regarding SSN capture/informed consent. | Should be working on resolution on SSN piece. We are required to have in place by fall. Please confirm with Matthew that is the case. If handled by your registrar’s office, remove the box on the form so there will be no contradiction. | MCs should let Matthew know their plan re: SSNs. BC will send out a template |
| Co-Grantee Spotlight: Bellevue College Esther Daniels | Curriculum: - CAHIMS and DA Certificates have been approved by campus CAC, DA waiting for approval by state board, expect July approval - Just submitted CAHIMS to VA for approval; DA will go in as soon as approved by state board. - Just found out that certificates need to be approved by DOE for financial aid and there is a 24 credit minimum, so CAHIMS will not be approved for financial aid; DA will go in as soon as approved by state board. - Looking at sequence of classes, when they’re offered, prereqs, etc. Marketing: - Student website up, CAHIMS certificate information up - Getting ready to send cert information through social media (LI, twitter, etc.) - Email blasts to orgs and groups Recruiting: - Have been to many events both to recruit and network (build relationships with recruiters, organization hr depts.) - Job fairs have been receiving lots of interest, but little response from prospective students so far - Transfer fair not so successful—light turnout, but higher hopes for fall fair Student Support: - Interviewing candidates for instructional support specialist - FB page, not used much for now, but ready to go - Survey—probably SM, use ideas from survey feedback from last Q |  |
| PM Meeting Survey Patricia & All | Results attached to agenda email Please take a look at these and send Patricia an email with items you feel most strongly about and include action item by Friday. We want to serve you. | MCs: Please take a look at these and send Patricia an email with items you feel most strongly about and include action item by Friday. |
| What Else? | We would like to have MCs facilitate the meetings. BC will make sure you have any information you need prior to the meeting. |  |