Health e Workforce Consortium PM Meeting

September 19, 2013     Onsite: V2071

Web Ex :

https://bellevuecollege.webex.com/bellevuecollege/j.php?ED=265252667&UID=1629567297&PW=NNDVkNDE0NDZm&RT=MiM0
Call-in toll number: 1-650-479-3208, 623 846 935#

AGENDA

| Invited: Toni Mariani; Cindy Woods; Lynnette Bennett; Gregg Sapp; Robert Foley; Donna Moran; Maria Anastario; Rachele Bakic; Esther Daniels; Helen Andries; Patricia Dombrowski; Matt Kenna; Margaret Murphy; Brooke MacKenzie; Andy Brucia; Nicole Bunselmeyer; Nathan Savage; Michele Royer; Roger Adams; Kelly Paustain; Jennifer Hemler; Debbie Kogan |  |  |
| --- | --- | --- |
| Agenda Items | Discussion | Action |
| Greetings from PM Facilitator Maria Anastario |  |  |
| Articulation Agreements All | “Show of hands if you’re working through the articulation agreement”: - Maria raised hand - Lynnette, Gregg, Rob: hand ‘half-raised’ (programs are changing as we speak) |  |
| Evaluation Visit by SPR Debbie Kogan or Renton, BC, Pierce PM’s | Debbie Kogan: We were pleased with our visit – learned a great deal about Health IT Education. Will be digesting what they’ve learned for the next 3-4 weeks. Esther: Had a great visit with them, answered lots of questions and we enjoyed talking to them. |  |
| Curriculum Specialist Position Ending All - Are some colleges keeping their Curriculum Development Specialist? - Comments feedback regarding position? - Was there an activity that the CD Specialist created that was exceptional that you would like to share? | Keeping CD specialist: - Rob: Ongoing work from CDS - Lynnette: Vivian started last January and we’ve extended her until December. Rolled over extra money to pay her on a contract to complete continuous improvement work once we’ve had a chance to use our materials. She’s been doing a great job. - Gregg: Our CDS was working on 3 different grants and it was difficult to get his time/attention. Keeping him through fall quarter so we can rearrange his work load. Anticipating that a lot of revisions are going to be in order. - Esther: CDS is done first week of November – position ending. Have Nursing PowerPoint’s that have been created on the HITEducation.org site. - Maria: CDS is still working away – 20 hours a week has proven to be insufficient. She came up with the curriculum and will be teaching it as well. |  |
| Fall Start / End of first year of grant All - Status of enrollment for Fall grant programs? - State a positive impact in regards to the grant being implemented at your college? - Biggest headache / challenge with the grant? | Status of enrollment: - Esther: low enrollment. Infusion classes are full. Hoping to continue adding students through the next couple days. CAHIMS starts this fall. Positive impact: Having support services for the students have been positive – able to help them with transition into employment. Waiting to see the impact of the instructional support position. - Gregg: We’ve got a full cohort of 20 students starting in the hemodialysis program. Small waiting list too. Winter quarter, starting a new cohort that’ll target veterans. We’d like to get a 100% veteran cohort. Positive impact: we are flexible to the faculties request for more hands-on material, not just watching PowerPoints. - Lynnette: Rad tech program is full. New Health IT Cert has 11 students. Nursing department rcv’d 3rd round of TAACCCT grant. Positive impact: Everyone is excited about the health IT certificate. Focusing on PLA and veterans has been something people on campus that people have been wanting to work toward. - Maria: At the moment everything is good. Full programs and waitlists. Positive impact: We were working in silos here, Health IT certificate has begun breaking down those silos – starting to see it our policy manual used by others. - Rob: (had to leave meeting) Biggest Headache/challenge: - Esther: Recruiting. Trying to find the right target for our certificates. We are getting closer to a decision on this. - Lynnette: Working with faculty – getting their time, achieving understanding of expectations/grant outcomes. - Gregg: Hiring a program navigator. Has been a big headache getting this done - administrative issues. - Maria: All staff members are different – union/non-union. Unsure how to properly utilize them. Involves dealing with various HR issues. | Lynnette Question: Can we enroll the same students in two different TAACCCT grants? |
| Updates from Bellevue *CIC *Annual Reporting *Rollover Requests * DoL Request in Process:Veterans PM & In person meeting at Bellevue | CIC: Attendance problem at the CIC meeting. This isn’t optional: it is written into the grant and it is a deliverable. Annual Reporting: End of Sept is the end of year one. Rollover Requests: Thanks from Helen for getting those in. They’re being reviewed. Veteran’s PM: Trying to complete moving funding for Veteran’s PM position to BC. Also trying to get funding to hold an in-person meeting at BC. Waiting to hear back on both items. | All: Send Patricia thoughts on how to improve attendance in the Continuous Improvement Cabinet. All: Will send out Narrative document tomorrow (Friday 9/20) and Excel form to enter in required data. Send Matt reporting information in October. Questions? Contact Matt. If interested in participating in Veteran’s or PLA Transition council / workgroup, contact Andy. They’re very eager to had people participate. |